## Project Plan
KOA v4 Implementation Tracker and Weekly Gantt Plan | Project Tracker and Weekly Gantt Plan | Project Tracker and Weekly Gantt Plan | Project Tracker and Weekly Gantt Plan | Project Tracker and Weekly Gantt Plan | Project Tracker and Weekly Gantt Plan | Project Tracker and Weekly Gantt Plan | Project Tracker and Weekly Gantt Plan | Project Tracker and Weekly Gantt Plan | Project Tracker and Weekly Gantt Plan | Project Tracker and Weekly Gantt Plan | Project Tracker and Weekly Gantt Plan | Project Tracker and Weekly Gantt Plan | Project Tracker and Weekly Gantt Plan | Project Tracker and Weekly Gantt Plan | Project Tracker and Weekly Gantt Plan | Project Tracker and Weekly Gantt Plan | Project Plan | Project Plan | Project Plan | Project Plan | Project Plan | Project Plan | Project Plan | Project Plan | Project Plan | Project Plan | Project Plan | Project Plan
PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE |  | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE
Project Title | KOA Website v4 | Aurora Launch | Aurora Launch | Project Manager |  | Oliver P + Codex | Jordan Lee |  | TOTAL TASKS | TOTAL TASKS | TOTAL TASKS | TOTAL TASKS | COMPLETE | COMPLETE | COMPLETE | COMPLETE | IN PROGRESS | IN PROGRESS | IN PROGRESS | IN PROGRESS | AT RISK | AT RISK | AT RISK | AT RISK | P0 TASKS | P0 TASKS | P0 TASKS | P0 TASKS
Company Name | Karen Organization of America | Northstar Labs | Northstar Labs | Timeline Start |  | 2026-08-10 | 2026-07-06 |  | 30 |  |  |  | 2 |  |  |  | 24 |  |  |  | 3 |  |  |  | 26
WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN |  | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW
Workstream | Task | Owner | Status | Priority | Start Date | End Date | Days |  | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21
Foundation | Reconcile v4 SPEC and IDEAS boundaries | Codex swarm | Complete | P0 | 2026-08-10 | 2026-08-10 | 1 | bar: 2026-08-10
Foundation | Preserve and map the existing KOA visual system | Codex swarm | Complete | P0 | 2026-08-10 | 2026-08-10 | 1 | bar: 2026-08-10
Foundation | Build bilingual route shell and language toggle | Codex swarm | In Progress | P0 | 2026-08-10 | 2026-08-16 | 7 | bar: 2026-08-10
Foundation | Implement reusable accessible design components | Codex swarm | In Progress | P0 | 2026-08-10 | 2026-08-16 | 7 | bar: 2026-08-10
Foundation | Create D1 schema, migration, audit logging, and roles | Codex swarm | In Progress | P0 | 2026-08-10 | 2026-08-16 | 7 | bar: 2026-08-10
Dictionary | Build dictionary browse, search, and filters | Codex swarm | In Progress | P0 | 2026-08-17 | 2026-08-23 | 7 | bar: 2026-08-17
Dictionary | Build bilingual dictionary entry detail | Codex swarm | In Progress | P0 | 2026-08-17 | 2026-08-23 | 7 | bar: 2026-08-17
Dictionary | Implement definitions, variants, relations, and examples | Codex swarm | In Progress | P0 | 2026-08-17 | 2026-08-30 | 14 | bar: 2026-08-17 to 2026-08-24
Dictionary | Implement contribution and moderation workflow | Codex swarm | In Progress | P0 | 2026-08-24 | 2026-09-06 | 14 | bar: 2026-08-24 to 2026-08-31
Dictionary | Implement R2 audio recording and upload metadata | Codex swarm | In Progress | P0 | 2026-08-24 | 2026-09-06 | 14 | bar: 2026-08-24 to 2026-08-31
Dictionary | Build contributor profiles and review status | Codex swarm | In Progress | P1 | 2026-08-31 | 2026-09-06 | 7 | bar: 2026-08-31
Translation | Publish translation and interpretation services | Codex swarm | In Progress | P0 | 2026-09-07 | 2026-09-13 | 7 | bar: 2026-09-07
Translation | Build approved interpreter directory and filters | Codex swarm | In Progress | P0 | 2026-09-07 | 2026-09-20 | 14 | bar: 2026-09-07 to 2026-09-14
Translation | Implement service request and booking intake | Codex swarm | In Progress | P0 | 2026-09-14 | 2026-09-20 | 7 | bar: 2026-09-14
Translation | Add court partnership intake and safety copy | Codex swarm | In Progress | P1 | 2026-09-14 | 2026-09-20 | 7 | bar: 2026-09-14
Community | Build community hub, stories, and events | Codex swarm | In Progress | P1 | 2026-09-21 | 2026-09-27 | 7 | bar: 2026-09-21
Community | Build moderated community board | Codex swarm | In Progress | P0 | 2026-09-21 | 2026-10-04 | 14 | bar: 2026-09-21 to 2026-09-28
Community | Implement feature, service, and collaboration requests | Codex swarm | In Progress | P0 | 2026-09-28 | 2026-10-04 | 7 | bar: 2026-09-28
Community | Build donation intent and receipt-safe workflow | Codex swarm | In Progress | P0 | 2026-09-28 | 2026-10-04 | 7 | bar: 2026-09-28
AI Pipeline | Store validated training pairs and consent records | Codex swarm | In Progress | P0 | 2026-10-05 | 2026-10-11 | 7 | bar: 2026-10-05
AI Pipeline | Implement dataset export and training job manifests | Codex swarm | In Progress | P1 | 2026-10-05 | 2026-10-18 | 14 | bar: 2026-10-05 to 2026-10-12
AI Pipeline | Implement human feedback API and metrics logging | Codex swarm | In Progress | P0 | 2026-10-12 | 2026-10-18 | 7 | bar: 2026-10-12
AI Pipeline | Build admin moderation and training dashboards | Codex swarm | In Progress | P0 | 2026-10-12 | 2026-10-25 | 14 | bar: 2026-10-12 to 2026-10-19
Launch | Add sitemap, robots, structured data, and hreflang | Codex swarm | In Progress | P0 | 2026-10-26 | 2026-11-01 | 7 | bar: 2026-10-26
Launch | Run automated accessibility and route coverage checks | Codex swarm | In Progress | P0 | 2026-10-26 | 2026-11-01 | 7 | bar: 2026-10-26
Launch | Run production build and fix integration defects | Codex swarm | In Progress | P0 | 2026-11-02 | 2026-11-08 | 7 | bar: 2026-11-02
Launch | Confirm source permissions and approved reviewers | Oliver P | At Risk | P0 | 2026-08-10 | 2026-11-08 | 91 | bar: 2026-08-10 to 2026-11-02
Launch | Confirm interpreters, court partners, and liability path | Oliver P | At Risk | P0 | 2026-08-10 | 2026-11-08 | 91 | bar: 2026-08-10 to 2026-11-02
Launch | Select donation processor and confirm receipt language | Oliver P | At Risk | P0 | 2026-08-10 | 2026-11-08 | 91 | bar: 2026-08-10 to 2026-11-02
Launch | Approve and publish the verified Sites version | Oliver P | Not Started | P0 | 2026-11-09 | 2026-11-15 | 7 | bar: 2026-11-09
Update Status, Priority, Start Date, and End Date as implementation decisions are confirmed. Red items need KOA approval or external evidence before launch. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use.
Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use. | Tip: edit yellow profile fields or the task table. Start Date, End Date, Status, and Priority drive duration, launch pulse, and weekly Gantt. Blank or invalid date rows stay unformatted. Synthetic illustrative data for template use.